## PSM I Course_Question Bank_v1.0
No | Question | Type | Answer Option 1 | Answer Option 2 | Answer Option 3 | Answer Option 4 | Answer Option 5 | Answer Option 6 | Answer | Explanation
1 | When is a Sprint over? | multiple-choice | When all Product Backlog items meet their definition of done. | When the Product Owner says it is done. | When all the tasks are completed. | When the time-box expires. |  |  | 4 | The duration of a Sprint is fixed and cannot be shortened or lengthened.
2 | What is the order of items in the Product Backlog? | multiple-choice | Alphabetical. | The recently added items at the top. | The less clear items at the top. | Less valuable and most unclear items at the bottom. |  |  | 4 | The Product Owner is responsible for placing the most valuable and clear items at the top of the Product Backlog.
3 | It is a good practice to have at least two Product Owners on big projects. | multiple-choice | TRUE | FALSE |  |  |  |  | 2 | The Product Owner is one person, not a committee, but the Product Owner may represent the desires of a committee in the Product Backlog.
4 | Definition of Done can be reviewed and adapted during each Sprint Retrospective. True or False? | multiple-choice | TRUE | FALSE |  |  |  |  | 1 | During each Sprint Retrospective, the Scrum Team plans ways to increase product quality by improving work processes or adapting the definition of "Done", if appropriate and not in conflict with product or organizational standards.
5 | The Scrum Master does the following regarding the Daily Scrum (select all applicable variants): | multi-select | Is responsible for conducting the Daily Scrum. | Teaches the Development Team to keep the Daily Scrum within the 15-minute time-box. | Ensures that the Development Team has the meeting. | If others are present at the Daily Scrum, ensures that they do not disrupt the meeting. | Manage the meeting in a way that each team member has a chance to speak. | All answers apply. | 2,3,4 | The Scrum Master: Ensures that the Development Team has the meeting, but the Development Team is responsible for conducting the Daily Scrum; Teaches the Development Team to keep the Daily Scrum within the 15-minute time-box; If others are present at the Daily Scrum, ensures that they do not disrupt the meeting.
6 | The Daily Scrum time-box depends on the size of the Development team. | multiple-choice | TRUE | FALSE |  |  |  |  | 2 | The Daily Scrum is a 15-minute time-boxed event for the Development Team of any size.
7 | Which answer best describes the topics covered in Sprint Planning? | multiple-choice | What can be done and how to do it. | What went wrong in the last Sprint and what to do differently this Sprint. | Who is on the team and what team member roles will be. | What to do and who will do it. | How conditions have changed and how the Product Backlog should evolve. |  | 1 | Sprint Planning answers the following: What can be delivered in the Increment resulting from the upcoming Sprint? & How will the work needed to deliver the Increment be achieved?
8 | What is the result of the Sprint Review? | multiple-choice | Common understanding of what can be delivered in the Increment and how will the work needed to deliver the Increment be achieved. | Common understanding of progress toward the Sprint Goal and how progress is trending toward completing the work in the Sprint Backlog. | A revised Product Backlog that defines the probable Product Backlog items for the next Sprint. | A list of improvements that the Scrum Team will implement in the next Sprint. |  |  | 3 | The result of the Sprint Review is a revised Product Backlog that defines the probable Product Backlog items for the next Sprint. The Product Backlog may also be adjusted overall to meet new opportunities.
9 | Which of the following are feedback loops in Scrum (Choose 3 answers)? | multi-select | Daily Scrum. | Sprint Review. | Release Planning. | Sprint Retrospective. | Refinement Meeting. |  | 1,2,4 | Daily Scrum, Sprint Review, Sprint Retrospective are opportunities for inspection & adaptation
10 | Every Development Team should have: | multiple-choice | The competencies and skills needed to deliver a Done Increment in a Sprint. | At least one representative from each major software engineering discipline (like QA, Dev, UX) | One Lead Developer and no more than 8 other members. |  |  |  | 1 | This is cross-functional.
11 | The maximum length of the Sprint Review (its time-box) is: | multiple-choice | 2 hours. | 4 hours for a monthly Sprint. For shorter Sprints it is usually shorter. | As long as needed. | 1 day. | 4 hours and longer as needed. |  | 2 | Sprint Review is a four-hour time-boxed meeting for onemonth Sprints. For shorter Sprints, the event is usually shorter.
12 | Why does a Development Team need a sprint goal? | multiple-choice | Sprint goals are not valuable. Everything is known from the Product Backlog. | The Development Team is more focused with a common yet specific goal. | A sprint goal only gives purpose to sprint 0. | A sprint goal ensures that all of the Product Backlog Items selected for the sprint are implemented. |  |  | 2 | The Sprint Goal is an objective that will be met within the Sprint through the implementation of the Product Backlog, and it provides guidance to the Development Team on why it is building the Increment.
13 | At the start of the Sprint Planning meeting, select the best description of the Product Backlog Items that the Product Owner wants to have done. | multiple-choice | They are stated as user stories and cannot be epic. | They are stated as user stories or use cases and test cases must have been identified for acceptance. | They are clearly stated, refined and understood by Product Owner and the Development Team such that a forecast of items can be made to implement the Sprint Goal. | They are fully described as User Stories or use cases already decomposed into tasks that will require no more than one-person day to complete by Development Team. |  |  | 3 | Items are clearly stated, refined and understood by Product Owner and the Development Team such that a forecast of items can be made to implement the Sprint Goal.
14 | Which does a self-organizing Development Team choose? | multiple-choice | How to best accomplish this work. | Product Backlog ordering. | Stakeholders for Sprint Review. | Sprint length. | When to release based on its progress. |  | 1 | They are self-organizing. No one (not even the Scrum Master) tells the Development Team how to turn Product Backlog into Increments of potentially releasable functionality;
15 | What does Burn-down Chart show? | multiple-choice | The evolution of the amount of uncertainty during a project. | How much work remains till the end of the Sprint. | Dependencies, start times and stop times for project tasks. | Hierarchy of tasks that comprise a project. |  |  | 2 | Burn-down chart shows the evolution of remaining effort against time.
16 | Who is responsible for coping with incomplete artifact transparency? | multiple-choice | The Product Owner | The Scrum Master | The Development Team | The Scrum Team |  |  | 2 | The Scrum Master’s job is to work with the Scrum Team and the organization to increase the transparency of the artifacts. This work usually involves learning, convincing, and change.
17 | Which two (2) things does the Development Team not do during the first Sprint? | multi-select | Deliver an increment of potentially shippable functionality. | Nail down the complete architecture and infrastructure. | Develop and deliver at least one piece of functionality. | Develop a plan for the rest of the project. |  |  | 2,4 | The heart of Scrum is a Sprint, a time-box of one month or less during which a “Done”, useable, and potentially releasable product Increment is created.
18 | An organization has decided to adopt Scrum, but management wants to change the terminology to fit with terminology already used. What will likely happen if this is done? | multiple-choice | Without a new vocabulary as a reminder of the change, very little change may actually happen. | The organization may not understand what has changed with Scrum and the benefits of Scrum may be lost. | Management may feel less anxious. | All answers apply. |  |  | 4 | All answers apply.
19 | Every Scrum Team must have a Product Owner and Scrum Master | multiple-choice | Yes, and they must be 100% dedicated to each team. | Yes, and each Scrum Team’s performance may be affected by their degree of participation as influenced by any other responsabilities (e.g. other teams for which they are also the SM or PO). | No . |  |  |  | 2 | The Scrum Team consists of a Product Owner, the Development Team, and a Scrum Master.
20 | A Scrum Master is working with a Development Team that has members in different physical locations. The Development Team meets in a variety of meeting rooms and has much to do logistically (for example, set up conference calls) before beginning the Daily Scrum. What action should the Scrum Master take ? | multiple-choice | Inform management and ask them to solve it. | Allow the Development Team to self-manage and determine for itself what to do. | Set up the meeting and tell the Development Team that is how it will be done. | Ask the Development Team members to alternate who is responsible for meeting setup. |  |  | 2 | The Scrum Master ensures that the Development Team has the meeting, but the Development Team is responsible for conducting the Daily Scrum.
21 | While under development the environment in which a product will be used changed. What is the effect on the product backlog? | multiple-choice | It is archived and a new Product Backlog is created to take its place. | There is no effect, because it has to stay the same until the end of the project. | It evolves to reflect what the product needs to be most valuable | It is converted into a requirements specification to ensure stability |  |  | 3 | It is the best answer, since it is true that a Product Backlog should evolve to reflect the greatest possible product value. Other options is not correct since, we don't archive a Product Backlog because of a change in a product environment; an answer implies that a Product Backlog stays unchanged until the end of a project, which is incorrect; there is nothing to indicate that the "requirements specification" alluded to will be more stable.
22 | All work to be done by Development Team must ultimately originate from Product Backlog? | multiple-choice | TRUE | FALSE |  |  |  |  | 1 | All work to be done by Development Team must ultimately originate from Product Backlog.
23 | Which of the following is required by Scrum ? | multi-select | Sprint restrospective. | Members must stand up at the Daily Scrum. | Sprint Burndown Chart. | Release Planning. | All options are correct. |  | 1 | Sprint restrospective.
24 | What does the word "development" mean in the context of Scrum? Select the best option. | multiple-choice | Development of an operational environment for the Product. | Product development, its releasing and sustaining. | Software and hardware development. | Research and identifying of viable markets, technologies, and Product capabilities. | Complex work that can include all the suggested options and even more |  | 5 | When the words "develop" and "development" are used in the Scrum Guide, they refer to complex work including software and hardware development, development and releasing of products and enhancements, development and sustaining product operational environments, research and identifying of viable markets and technologies, and even more.
25 | The time-box for the Sprint Planning meeting is? | multiple-choice | 4 hours. | 8 hours for a monthly Sprint. For shorter Sprints it is usually shorter. | Whenever it is done. | Monthly. |  |  | 2 | Sprint Planning is time-boxed to a maximum of eight hours for a one-month Sprint. For shorter Sprints, the event is usually shorter.
26 | How does the Scrum Master help the Product Owner? Select the three most appropriate answers. | multi-select | Understanding product planning in an empirical environment. | Facilitating Scrum events as requested or needed. | Introducing cutting edge development practices. | Finding techniques for effective Product Backlog management. | Leading and coaching the organization in its Scrum adoption. |  | 1,2,4 | The Scrum Master serves the Product Owner in several ways, including: Ensuring that goals, scope, and product domain are understood by everyone on the Scrum Team as well as possible; Finding techniques for effective Product Backlog management; Helping the Scrum Team understand the need for clear and concise Product Backlog items; Understanding product planning in an empirical environment; Ensuring the Product Owner knows how to arrange the Product Backlog to maximize value; Understanding and practicing agility; and Facilitating Scrum events as requested or needed.
27 | What is the role of Management in Scrum? | multiple-choice | Continually monitor staffing levels of the Development Team. | Monitor the Development Team's productivity. | Support the Product Owner with insights and information into high value product and system capabilities. Support the Scrum Master to cause organizational change thatfosters empiricism, self-organization, bottom-up intelligence, and intelligent release of software. | Identify and remove people that aren't working hard enough. |  |  | 3 | Management has no active role in the actual product development through Scrum. However, management external to the Scrum team is incredibly important in setting the vision and strategy to guide the overall direction of the organization.
28 | Who is responsible for managing the progress of work during a Sprint? | multiple-choice | The Development Team | The Development Team | The Development Team | The Development Team |  |  | 1 | The Development Team uses the Daily Scrum to inspect progress toward the Sprint Goal and to inspect how progress is trending toward completing the work in the Sprint Backlog.
29 | What happens during the Sprint? Select three answers. | multi-select | No changes are made that would endanger the Sprint Goal. | Scope may be clarified and re-negotiated between the Product Owner and Development Team as more is learned. | Sprint scope is defined at the Sprint Planning and cannot be changed. | Quality goals do not decrease. | The Sprint Goal is changed frequently to reflect the status of the remaining work. |  | 1,2,4 | During the Sprint: No changes are made that would endanger the Sprint Goal; Quality goals do not decrease; and Scope may be clarified and re-negotiated between the Product Owner and Development Team as more is learned.
30 | What are the characteristics of a Development Team? Select three most appropriate choices. | multi-select | Having at least one test engineer in the Development Team | Accountability belongs to the Development Team as a whole | Scrum recognizes no sub-teams in the Development Team | Scrum recognizes no titles for Development Team members other than Developer | Having the Scrum Master as a part-time Developer in the Development Team |  | 2,3,4 | Development Teams have the following characteristics: They are self-organizing. No one (not even the Scrum Master) tells the Development Team how to turn Product Backlog into Increments of potentially releasable functionality; Development Teams are cross-functional, with all of the skills as a team necessary to create a product Increment; Scrum recognizes no titles for Development Team members other than Developer, regardless of the work being performed by the person; there are no exceptions to this rule; Scrum recognizes no sub-teams in the Development Team, regardless of particular domains that need to be addressed like testing or business analysis; there are no exceptions to this rule; and Individual Development Team members may have specialized skills and areas of focus, but accountability belongs to the Development Team as a whole.
31 | What is the main reason for the Scrum Master to be at the Daily Scrum? | multiple-choice | To make sure every team member answers the three questions. | He or she does not have to be there; he or she only has to ensure the Development Team has a Daily Scrum. | To write down any changes to the Sprint Backlog, including adding new items, and tracking progress on the burn-down. | To gather status and progress information to report to management. |  |  | 2 | The Scrum Master enforces the rule that only Development Team members participate in the Daily Scrum.
32 | What is the Sprint Retrospective? | multiple-choice | It is the key inspect and adapt meeting. | It is a meeting where the Development Team synchronizes activities and creates a plan for the next 24 hours. | It is a meeting to inspect the Increment and adapt the Product Backlog if needed. | It is an opportunity for the Scrum Team to inspect itself and create a plan for improvements to be enacted during the next Sprint. |  |  | 4 | The Sprint Retrospective is an opportunity for the Scrum Team to inspect itself and create a plan for improvements to be enacted during the next Sprint.
33 | It is a good practice to have from time to time a special technical Sprint that consists only of tasks removing the technical debt without implementing any new functionality. | multiple-choice | TRUE | FALSE |  |  |  |  | 2 | It is prohibited. The purpose of each Sprint is to deliver Increments of potentially releasable functionality that adhere to the Scrum Team’s current definition of "Done."
34 | Scrum is not a process or technique. True or False? | multiple-choice | TRUE | FALSE |  |  |  |  | 1 | Scrum is not a process, technique, or definitive method. Rather, it is a framework within which you can employ various processes and techniques.
35 | During the Sprint Review, is up to the Stakeholders to reorder the Product Backlog. | multiple-choice | TRUE | FALSE |  |  |  |  | 2 | Only PO can reorder Product Backlog items.
36 | In which meetings the Key Stakeholders are allowed to participate? | multi-select | The Sprint Retrospective | The Sprint Planning | The Sprint Review | The Daily Scrum |  |  | 3 | The Key Stakeholders are allowed to participate only in the Sprint Review meeting. However, any member of the Scrum Team can interact with them any time.
37 | Scrum Master is keeping a list of open impediments, but it is growing and he/she has been able to resolve only a small portion of the impediments. Which three techniques would be most helpful in this situation? | multi-select | Prioritize the list and work on them in order. | Alert management to the impediments and their impact. | Arrange a triage meeting with all other project managers. | Discuss the absence of management support with the Development Team. | Tell the Product Owner that Scrum isn't working. | Consult with the Development Team. | 1,2,6 | The Scrum Master section in Scrum Guide
38 | Who participates in the Sprint Review? Select all applicable variants. | multi-select | The Scrum Master | The Product Owner | The Key Stakeholders | The Development Team | The Organization CEO |  | 1,2,3,4 | During the Sprint Review, the Scrum Team and stakeholders collaborate about what was done in the Sprint. Based on that and any changes to the Product Backlog during the Sprint, attendees collaborate on the next things that could be done to optimize value.
39 | The Development Team should have all the skills needed to: | multiple-choice | Complete the project as estimated when the date and cost are committed to the Product Owner. | Do all of the development work, except for specialized testing that requires additional tools and environments. | Turn the Product Backlog items it selects into an increment of potentially shippable product functionality. |  |  |  | 3 | The Development Team consists of professionals who do the work of delivering a potentially releasable Increment of "Done" product at the end of each Sprint. Development Teams are cross-functional, with all of the skills as a team necessary to create a product Increment.
40 | What are the three pillars that uphold Scrum? | multi-select | Transparency | Self-organization | Adaptation | Agility | Inspection | Cross-functionality | 1,3,5 | Scrum is founded on empirical process control theory, or empiricism. Empiricism asserts that knowledge comes from experience and making decisions based on what is known. Three pillars uphold every implementation of empirical process control: transparency, inspection, and adaptation.
41 | Scrum is founded on | multiple-choice | Empiricism | Empirical criticism | Common sense | Kanban system |  |  | 1 | Scrum is founded on empirical process control theory, or empiricism. Empiricism asserts that knowledge comes from experience and making decisions based on what is known.
42 | Who is required to attend the Daily Scrum? | multi-select | The Scrum Master | The Development Team | The Product Owner | The Key Stakeholders |  |  | 2 | Only the people doing the work described on the Sprint Backlog need to inspect and adapt at the Daily Scrum. If the Scrum Master or Product Owner is also on the Development Team, they will need to be at the Daily Scrum. Otherwise, the Scrum Master simply has to make sure the Development Team knows how to conduct a Daily Scrum and does so.
43 | Who has the authority to cancel the Sprint? | multiple-choice | The Product Owner. | The Scrum Master. | The Product Owner and the Scrum Master. | The Key Stakeholders. | The Development Team. |  | 1 | Only the Product Owner has the authority to cancel the Sprint, although he or she may do so under influence from the stakeholders, the Development Team, or the Scrum Master.
44 | Who is responsible for all estimates in the Product Backlog? | multiple-choice | The Scrum Team | The Product Owner | The Development Team | The Scrum Master and the Development Team | The Product Owner and the Development Team | The Scrum Master | 3 | The Development Team is responsible for all estimates in the Product Backlog. The Product Owner may influence the Development Team by helping it understand and select trade-offs, but the people who will perform the work make the final estimate.
45 | Select the five Scrum Values. | multi-select | Focus | Openness | Courage | Commitment | Respect | Self-organization | 1,2,3,4,5 | The Scrum Guide recognizes the following Scrum Values: commitment, courage, focus, openness and respect.
46 | What are the two primary ways a Scrum Master keeps a Development Team working at its highest level of productivity? | multi-select | By facilitating Development Team decisions. | By removing impediments that hinder the Development Team. | By ensuring the meetings start and end at the proper time. | By keeping high value features high in the Product Backlog. |  |  | 1,2 | A Scrum Master is a servant-leader for the Development Team. Facilitation and removing impediments serves a team in achieving the best productivity possible.
47 | Who is responsible for crafting the Sprint Goal at the Sprint Planning? | multiple-choice | The Scrum Team. | The Product Owner. | The Development Team. | The Scrum Master. | The Key Stakeholders. |  | 1 | After the Development Team forecasts the Product Backlog items it will deliver in the Sprint, the Scrum Team crafts a Sprint Goal.
48 | When many Scrum teams are working on the same product, should all of their increments be integrated every Sprint? | multiple-choice | Yes, but only for Scrum teams whose work has dependencies. | Yes, otherwise the Product Owners (and stakeholders) may not be able to accurately inspect what is done. | No, each Scrum team stands alone. | No, that is far too hard. | How conditions have changed and how the Product Backlog should evolve. |  | 2 | It provide rapid assurance that defects and configuration management issues have not been introduced.
49 | What are the responsibilities of a tester in a development Team (choose 2)? | multi-select | There is no specific tester role. | Finding bugs to assure quality. | Checking the work of the developers. | Everyone is responsible for quality in Scrum. |  |  | 1,4 | Scrum recognizes no titles for Development Team members, regardless of the work being performed by the person;
50 | What three factors are best considered when establishing the Sprint length? (Choose 3 answers). | multi-select | The ability to go to market with a product release. | Sprints must have the same length throughout an organization. | The frequency at which team formation can be changed. | The level of uncertainty over the technology to be used. | The risk of being disconnected from the stakeholders. |  | 1,4,5 | The bigger part of interaction with the Key Stakeholders happens at the Sprint Review meeting. If the Sprint length is bigger, this feedback loop becomes longer. Shorter Sprints is an effective way to hone in on the requirements or try out the technology before committing to a solution. Shorter Sprints suppose that the Dev Team produces “done” increments more frequently. It allows the PO to release the increments more frequently too.
51 | If an inspector determines that one or more aspects of a process deviate outside acceptable limits, when must an adjustment be made? | multiple-choice | The deviations should be discussed at the Daily Scrum and then an adjustment must be made. | As soon as possible to minimize further deviation. | After clarifying all the details with the Product Owner. | After Scrum Master approval. |  |  | 2 | If an inspector determines that one or more aspects of a process deviate outside acceptable limits, and that the resulting product will be unacceptable, the process or the material being processed must be adjusted. An adjustment must be made as soon as possible to minimize further deviation.
52 | Who is responsible for registering the work estimates during a Sprint? | multiple-choice | he Development Team. | The Scrum Master. | The Product Owner. | The most junior member of the Team. |  |  | 1 | The Development Team self-organizes to undertake the work in the Sprint Backlog, both during Sprint Planning and as needed throughout the Sprint.
53 | Who should know the most about the progress toward a business objective or a release, and be able to explain the alternatives most clearly? | multiple-choice | The Product Owner | The Development Team | The Scrum Master | The Project Manager |  |  | 1 | The Product Owner is the sole person responsible for managing the Product Backlog, which includes that the Product Backlog is visible, transparent, and clear to all, and shows what the Scrum Team will work on next.
54 | Why is the Daily Scrum held at the same time and same place? | multiple-choice | The place can be named. | The consistency reduces complexity. | The Product Owner demands it. | Rooms are hard to book and this lets it be booked in advance. |  |  | 2 | The Daily Scrum is held at the same time and place each day to reduce complexity
55 | Development Team membership should change: | multiple-choice | Every Sprint to promote shared learning. | Never, because it reduces productivity. | As needed, while taking into account a short term reduction in productivity. | As needed, with no special allowance for changes in productivity. |  |  | 3 | Teams typically go through some steps before achieving a state of increased performance. Changing membership typically reduces cohesion, affecting performance and productivity in the short term.
56 | Which of these may a Development Team deliver at the end of a Sprint? | multi-select | An increment of working software that is "Done". | An increment of software with minor known bugs on it. | A single document, if that is what the Scrum Master asked for. |  |  |  | 1 | An increment is a body of inspectable, done work that supports empiricism at the end of the Sprint.
57 | The Product Owner determines how many Product Backlog items the Development Team selects for a Sprint. | multiple-choice | False, the Scrum Master does that. | False, capacity and commitment are the project manager’s responsibility. | True. | True, but only after confirmation by the resource manager that the Team has enough capacity. | False. | True, accordingly to what was committed to stakeholders. | 5 | The Development Team self-organizes to undertake the work in the Sprint Backlog, both during Sprint Planning and as needed throughout the Sprint.
58 | When is a Product Backlog item considered complete? | multiple-choice | When all work in the Sprint Backlog that is related to is complete. | At the end of the Sprint. | When QA reports that t passes all acceptance critea. | The item has no work remaining that must still be done be used by its end user. |  |  | 4 | When it has no work remaining that must still be done be used by its end user.
59 | When many Development Teams are working on a single product, what best describes the definition of "done?" | multiple-choice | Each Development Team defines and uses its own. The differences are discussed and reconciled during a hardening Sprint. | Each Development Team uses its own but must make their definition clear to all other Teams so the differences are known. | All Development Teams must have a definition of "done" that makes their combined work potentially releasable. | It depends. |  |  | 3 | Scrum requires an Increment to be releasable. This is an Increment of product. Many teams working on a single product are expected to deliver such an Increment.
60 | The CEO asks the Development Team to add a "very important" item to a Sprint that is in progress. What should the Development Team do? | multiple-choice | Add the item to the current Sprint without any adjustments. | Add the item to the current Sprint and drop an item of equal size. | Add the item to the next Sprint. | Inform the Product Owner so he/she can work with the CEO. |  |  | 4 | The items selected for a Sprint have been selected as most valuable with the Product Owner. The items serve the Sprint's goal. No changes should be made that endanger the Sprint Goal. No one external to the Scrum Team can force changes on the Development Team (Sprint Backlog) and the Product Owner (Product Backlog).
61 | Where can Scrum be used? Check all the applicable items. | multi-select | Development of software and hardware | Research and identifying of viable markets, technologies, and product capabilities | Development of products and enhancements | Development and sustaining of Cloud and other operational environments | Managing the operation of an organization | Development of almost everything we use in our daily lives as individuals and societies | 1,2,3,4,5,6 | Scrum has been used to develop software, hardware, embedded software, networks of interacting function, autonomous vehicles, schools, government, marketing, managing the operation of organizations and almost everything we use in our daily lives, as individuals and societies. Scrum has been used extensively, worldwide, to: Research and identify viable markets, technologies, and product capabilities; Develop products and enhancements; Release products and enhancements, as frequently as many times per day; Develop and sustain Cloud (online, secure, on-demand) and other operational environments for product use; and Sustain and renew products.
62 | Items on the Product Backlog tend to be: | multiple-choice | Larger than the items in the Sprint Backlog. | The same size as the items in the Sprint Backlog. | Smaller than the items in the Sprint Backlog. | It depends. |  |  | 1 | Higher ordered Product Backlog items are usually clearer and more detailed than lower ordered ones.
63 | Sprint Reviews are an opportune time to collect customer feedback. | multiple-choice | TRUE | FALSE |  |  |  |  | 1 | The result of the Sprint Review is a revised Product Backlog that defines the probable Product Backlog items for the next Sprint. The Product Backlog may also be adjusted overall to meet new opportunities.
64 | A Scrum Master is introducing Scrum to a new Development Team. The Development Team has decided that a retrospective is unnecessary. What action should the Scrum Master take? | multiple-choice | Comply with the decision of the self-organizing Team. | Consult with the Product Owner to see how he/she feels about the situation. | Begin facilitating productive, useful retrospectives. | Call a meeting between the Development Team and senior management. |  |  | 3 | Each component within the framework serves a specific purpose and is essential to Scrum’s success and usage.
65 | A new developer has joined an existing Scrum team. He/she is having continuing conflicts with existing members and is making the environment hostile. If necessary, who is responsible for removing the new team member, and why? | multiple-choice | Product Owner is responsible because he/she controls the return on investment (ROI) of the work. | The Development Team is responsible because it is a sef-organizing Team, although it may have to be advised by the Scrum Master. | Scrum Master is responsible because he/she needs to remove impediments. | The manager to whom he/she reports is responsible because he/she has authority for hiring and firing. |  |  | 3 | Removing impediments to the Development Team’s progress;
66 | What part of the capacity of the Development Team does Product Backlog refinement usually consume? | multiple-choice | Not more than 20% | Not more than 10% | The Development Team is not authorized for Product Backlog refinement | Not more than 5% |  |  | 2 | Product Backlog refinement usually consumes no more than 10% of the capacity of the Development Team.
67 | What are the three most applicable characteristics of the Product Owner? | multi-select | Lead Facilitator of Key Stakeholder Involvement. | Product Marketplace Expert. | Product Value Maximizer. | Lead Scrum evangelist in the Organization. | Facilitator of Scrum events. |  | 1,2,3 | Product Value Maximizer; Lead Facilitator of Key Stakeholder Involvement & Product Marketplace Expert.
68 | What does Cone of Uncertainty show? | multiple-choice | How much work remains till the end of the Sprint. | Dependencies, start times and stop times for project tasks. | Hierarchy of tasks that comprise a project. | How much is known about the Product over time. |  |  | 4 | The Cone of Uncertainty describes the evolution of the amount of uncertainty during a project.
69 | Which technique is the LEAST productive way for the Scrum Master to ensure that the Development Team communicates effectively with the Product Owner? | multiple-choice | Teach the Product Owner about the technologies employed during the Sprints. | Teach the Team to talk in terms of business needs and objectives. | Monitor communications between them. | Act as a go-between for them. |  |  | 4 | As the answer
70 | The Scrum Master should not allow the Product Owner to go to the Sprint Planning meeting without having already devised the Sprint Goal. | multiple-choice | TRUE | FALSE |  |  |  |  | 2 | Sprint Goald maded by Scrum Team
71 | What is the role of Product Owner in crafting the Sprint Goal | multiple-choice | The Product Owner should not come to the Sprint Planning without a clearly defined sprint goal. | The Product Owner should come to the Sprint Planning with a business objective in mind and work with Development Team to craft the sprint goal based upon the forecast. | The Product Owner has no role on it. This is Development Team´s responsibility. | The Product Owner describes the scope and therefore also the sprint goal. | The Product Owner must work with stakeholders to set the Sprint Goal. |  | 2 | During Sprint Planning the Scrum Team also crafts a Sprint Goal.
72 | The purpose of the Sprint Retrospective is to (select three): | multi-select | Identify and order the major items that went well and potential improvements. | Create a plan for implementing improvements to the way the Scrum Team does its work. | Get feedback from the Key Stakeholders invited by the Product Owner. | Get technical or domain advice from specialists invited by The Development Team or The Scrum Master. | Inspect how the last Sprint went with regards to people, relationships, process, and tools. |  | 1,2,5 | The purpose of the Sprint Retrospective is to: Inspect how the last Sprint went with regards to people, relationships, process, and tools; Identify and order the major items that went well and potential improvements; and Create a plan for implementing improvements to the way the Scrum Team does its work.
73 | What is the Increment? | multiple-choice | All items in the Sprint Backlog that could be released regardless of whether the Product Owner decides to actually do it. | The sum of all the Product Backlog items completed during the Sprint. | The sum of all the Product Backlog items completed during the Sprint and the value of the increments of all previous Sprints. | All "Done" items in the Sprint Backlog. |  |  | 3 | The Increment is the sum of all the Product Backlog items completed during the Sprint and the value of the increments of all previous Sprints.
74 | What is a Product Backlog work that a Product Owner might delegate? | multiple-choice | Write user stories. | Order Product Backlog. | Represent stakeholders to the Scrum Team. | Attend the Sprint Review. |  |  | 1 | The Product Owner may do Product Backlog management work, or have the Development Team do it. However, the Product Owner remains accountable.
75 | Which phrase best describes a Product Owner? | multiple-choice | Go-beetween between development team and customers. | Requirements engineer. | Value optimizer. | Team manager. |  |  | 3 | Value optimizer/maximizer
76 | Who is responsible for the Product Backlog? | multiple-choice | The Product Owner. | The Product Owner and The Development Team. | The Product Owner and The Scrum Master. | The Scrum Master. | The Scrum Master and The Development Team. | The Development Team. | 1 | The Product Owner is responsible for the Product Backlog, including its content, availability, and ordering.
77 | How many hours per day should a person on a Scrum team work? | multiple-choice | 14 hours. | A sustainable pace, usually from 7-8 hours per day. | An “ideal day” measuring only when he or she is productive. | However many hours are needed to get the work done. |  |  | 2 | A sustainable pace, usually from 7-8 hours per day.
78 | The Development Team is accountable for releasing the most valuable product possible. | multiple-choice | TRUE | FALSE |  |  |  |  | 2 | The PO is accountable for releasing the most valuable product possible.
79 | It is mandatory that the product increment be released to production at the end of each Sprint. | multiple-choice | TRUE | FALSE |  |  |  |  | 2 | The product increment should be usable and releasable at the end of every Sprint, but it does not have to be released.
80 | Who is responsible for the monitoring of the remaining work towards the Project Goal? | multiple-choice | The Scrum Master | The Scrum Master and The Development Team | The Scrum Team | The Product Owner and The Development Team | The Product Owner | The Development Team | 5 | The Product Owner tracks total work remaining at least every Sprint Review. The Product Owner compares this amount with work remaining at previous Sprint Reviews to assess progress toward completing projected work by the desired time for the goal. This information is made transparent to all stakeholders.
81 | An optimal Development Team has at least 5 members: | multiple-choice | To have enough coverage in case of illness or emergency. | To ensure high productivity. | To increase the reliability of their estimates. | This is not required as long as the overall team maturity is high. | This is not required in Scrum. |  | 5 | Optimal Development Team size is small enough to remain nimble and large enough to complete significant work within a Sprint. Fewer than three Development Team members decrease interaction and results in smaller productivity gains. Having more than nine members requires too much coordination. The Product Owner and Scrum Master roles are not included in this count unless they are also executing the work of the Sprint Backlog.
82 | Please, select a time-box for each Scrum event. | multiple-choice | Sprint Planning = 4 hours or less; Daily Scrum = 15 mins; Sprint Review = 8 hours or less; Sprint Retrospective = 3 hours or less. | Sprint Planning = 8 hours or less; Daily Scrum = 15 mins; Sprint Review = 3 hours or less; Sprint Retrospective = 4 hours or less. | Sprint Planning = 8 hours or less; Daily Scrum = 15 mins; Sprint Review = 4 hours or less; Sprint Retrospective = 3 hours or less. | Sprint Planning = 4 hours or less; Daily Scrum = 15 mins; Sprint Review = 3 hours or less; Sprint Retrospective = 8 hours or less. | Sprint Planning = 3 hours or less; Daily Scrum = 15 mins; Sprint Review = 4 hours or less; Sprint Retrospective = 8 hours or less. | Sprint Planning = 3 hours or less; Daily Scrum = 15 mins; Sprint Review = 8 hours or less; Sprint Retrospective = 4 hours or less. | 3 | Sprint Planning is time-boxed to a maximum of eight hours for a one-month Sprint. For shorter Sprints, the event is usually shorter. The Daily Scrum is a 15-minute time-boxed event for the Development Team to synchronize activities and create a plan for the next 24 hours. Sprint Review is a four-hour time-boxed meeting for one-month Sprints. For shorter Sprints, the event is usually shorter. Sprint Retrospective is a three-hour time-boxed meeting for one-month Sprints. For shorter Sprints, the event is usually shorter.
83 | How does Definition of "Done" help to the Scrum Team? Select the three most applicable items. | multi-select | DoD ensures artifact transparency. | DoD is used to assess when work is complete on the product Increment. | DoD helps in inspection and adaptation. | DoD helps to calculate velocity of the Scrum Team. | DoD guides the Development Team in knowing how many Product Backlog items it can select during a Sprint Planning. |  | 1,2,5 | DoD is used to assess when work is complete on the product Increment; DoD guides the Development Team in knowing how many Product Backlog items it can select during a Sprint Planning; DoD ensures artifact transparency.
84 | Which of the following are true about the Product Owner role? (Select all that apply) | multi-select | Multiple people can share the Product Owner role. | The Product Owner can be influenced by a committee. | The Product Owner role can be played by a committee or a team of people. | The Product Owner is one person. | The Product Owner is accountable for ordering the Product Backlog. |  | 2,4,5 | Product Owner section in Scrum Guide
85 | How much time is required after a sprint to prepare for the next Sprint? | multiple-choice | The break between Sprints is time-boxed to 1 week for 30 day Sprints, and usually less for shorter Sprints. | Enough time for the requirements for the next sprint to be determined and documented. | Enough time for the Development Team to finish the testing from the last Sprint. | None. A new sprint starts immediately after the last sprint. |  |  | 4 | A new sprint starts immediately after the last sprint.
86 | When multiple teams work together on the same product, each team should maintain a separate Product Backlog. | multiple-choice | TRUE | FALSE |  |  |  |  | 2 | Products have one Product Backlog, regardless of how many teams are used. Any other setup makes it difficult for the Development Team to determine what it should work on.
87 | What does it mean to say that an event has a time-box? | multiple-choice | The event must happen at a set time. | The event must happen by a given time. | The event must take at least a minimum amount of time. | The event can take no more than a maximum amount of time. |  |  | 4 | Time-boxed events are events that have a maximum duration.
88 | Definition of "Done" is created during the first Sprint and remains unchanged until the Product release. | multiple-choice | TRUE | FALSE |  |  |  |  | 2 | False. During each Sprint Retrospective, the Scrum Team plans ways to increase product quality by adapting the definition of "Done" as appropriate.
89 | What belongs solely to the Development Team? | multi-select | The Product Backlog | The Definition of Done | The Increment | The Sprint Backlog |  |  | 4 | Only the Development Team can change its Sprint Backlog during a Sprint. The Sprint Backlog is a highly visible, real-time picture of the work that the Development Team plans to accomplish during the Sprint, and it belongs solely to the Development Team.
90 | Which of the following is an example of an increment of working software? | multiple-choice | A decomposition of all Product Backlog into tasks for future Sprint Backlog lists. | Additional features in a useable state that complement those delivered in previous iterations. | A new user interface design for functionality delivered in previous iterations. | UML diagrams that describe how to deliver functionality. | An automated test suite to verify functionality delivered in previous iterations. |  | 2 | The Increment is the sum of all the Product Backlog items completed during a Sprint and the value of the increments of all previous Sprints.
91 | When might a Sprint be abnormally terminated? | multiple-choice | When it becomes clear that not everything will be finished by the end of the Sprint. | When the Development Team feels that the work is too hard. | When the sales department has an important new opportunity | When the Sprint Goal becomes obsolete. |  |  | 4 | A Sprint can be cancelled before the Sprint time-box is over. A Sprint would be cancelled if the Sprint Goal becomes obsolete. This might occur if the company changes direction or if market or technology conditions change.
92 | When does a Development Team make adjustments to its engineering practices? | multiple-choice | Prior to starting a project. | Before a Sprint begins. | Whenever needed. | During Sprint Planning. | After they have been discussed and agreed to at the Sprint Retrospective. |  | 3 | Whenever needed.
93 | The time-box for a Daily Scrum is? | multiple-choice | The same time of day every day. | Two minutes per person. | 4 hours. | 15 minutes. | 15 minutes for a 4 week sprint. For shorter Sprints it is usually shorter. |  | 4 | The length of a daily Scrum is fixed at 15 minutes, it does not change with the length of a Sprint.
94 | The structure of the Daily Scrum is well-defined and constant. Every team member should answer the three main questions: What did I do yesterday?; What will I do today? & Do I see any impediment? | multiple-choice | TRUE | FALSE |  |  |  |  | 2 | There is no any prescribed structure. The structure of the Daily Scrum is set by the Development Team and can be conducted in different ways if it focuses on progress toward the Sprint Goal. Some Development Teams will use questions, some will be more discussion based. It is still perfectly fine to use the questions, but other ways of conducting the meeting are also possible.
95 | What are the three main qualities the team model in Scrum is designed to optimize? | multi-select | Productivity | Flexibility | Creativity | Responsibility | Agility | Competence | 1,2,3 | The team model in Scrum is designed to optimize flexibility, creativity, and productivity.
96 | How does the Scrum Master serve the Development Team? Select the three most appropriate answers. | multi-select | Helping the Development Team to create high-value products. | Removing impediments to the Development Team’s progress. | Coaching the Development Team in self-organization and cross-functionality. | Helping the Development Team as the team leader. | Adding or removing developers from the Development Team in accordance with team velocity changes. |  | 1,2,3 | The Scrum Master serves the Development Team in several ways, including: Coaching the Development Team in self-organization and cross-functionality; Helping the Development Team to create high-value products; Removing impediments to the Development Team’s progress; Facilitating Scrum events as requested or needed; and Coaching the Development Team in organizational environments in which Scrum is not yet fully adopted and understood.
97 | Scrum does not allow additional meetings that are not defined in Scrum. | multiple-choice | TRUE | FALSE |  |  |  |  | 2 | Scrum allows additional meetings if they facilitate achieving the Sprint Goal.
98 | What are the Scrum Artifacts? Select all applicable items. | multi-select | Increment | Sprint Backlog | The list of removed impediments | Product Backlog | The Sprint Goal |  | 1,2,4 | The Scrum artifacts are Product Backlog, Sprint Backlog and Increment.
99 | The Definition of Done is used to: (Select three answers) | multi-select | Guide the Development Team on how many Product Backlog items to select in Sprint. | Create a shared understanding of when work is complete. | Describe the purpose, objective, and time-box of each Scrum Even. | Describe the work that must be done before the Sprint can be declared complete. | Increase transparency. |  | 1,2,5 | DoD section of Scrum Guide
100 | Which two activities will a Product Owner engage in during a sprint? | multi-select | Update the Sprint Burndown chart. | Prioritize the Development Teams work on the Sprint Backlog. | Run the Daily Scrum. | Answer questions from the Development Team about items in the current sprint. | Work with stakeholders. |  | 4,5 | Product Backlog management includes: Clearly expressing Product Backlog items; Ordering the items in the Product Backlog to best achieve goals and missions; Optimizing the value of the work the Development Team performs; Ensuring that the Product Backlog is visible, transparent, and clear to all, and shows what the Scrum Team will work on next; and Ensuring the Development Team understands items in the Product Backlog to the level needed.
101 | Which Scrum values are exhibited by not building a Product Backlog Items that have low business value? (Choose 3 answers) | multi-select | Focus. | Respect. | Courage. | Earned value. | Economic Value Added. |  | 1,2,3 | When the values of commitment, courage, focus, openness and respect are embodied and lived by the Scrum Team, the Scrum pillars of transparency, inspection, and adaptation come to life and build trust for everyone.
102 | What does Product Backlog management include? Select three most applicable items. | multi-select | Moving Product Backlog items into the Sprint Backlog. | Ensuring that the Product Backlog is visible, transparent, and clear to all, and shows what the Scrum Team will work on next. | Optimizing the value of the work the Development Team performs. | Presenting Product Backlog items to the Key Stakeholders. | Ordering the items in the Product Backlog to best achieve goals and missions. |  | 1,2,5 | Product Backlog management includes: Clearly expressing Product Backlog items; Ordering the items in the Product Backlog to best achieve goals and missions; Optimizing the value of the work the Development Team performs; Ensuring that the Product Backlog is visible, transparent, and clear to all, and shows what the Scrum Team will work on next; and Ensuring the Development Team understands items in the Product Backlog to the level needed.
103 | The Product Owner must write all the Product Backlog Items (user stories, non-functional requirements, etc.) on the Product Backlog before handing them over the Development Team. | multiple-choice | TRUE | FALSE |  |  |  |  | 2 | A Product Backlog is never complete. The earliest development of it lays out the initially known and best-understood requirements.
104 | The Scrum Master is focused primarily on the Scrum Team and usually does not care about those outside the Scrum Team. | multiple-choice | TRUE | FALSE |  |  |  |  | 2 | The Scrum Master is a servant-leader for the Scrum Team. The Scrum Master helps those outside the Scrum Team understand which of their interactions with the Scrum Team are helpful and which aren’t. The Scrum Master helps everyone change these interactions to maximize the value created by the Scrum Team.
105 | Which statement best describes the Sprint Backlog as outcome of the Sprint Planning? | multiple-choice | It is a list of the User Stories estimated in story points, and a list of corresponding tasks that are estimated in hours. | It is a task list where every Development Team member has signed up for all the tasks that he/she intends to do in the Sprint. | It is a decomposition of Product Backlog items such that enough work is decomposed for at least the first days of the Sprint. | It must be ordered by the Product Owner. | It is an exhaustive list of all tasks for the Sprint. Tasks must be estimated in hours. |  | 3 | The Sprint Backlog is the set of Product Backlog items selected for the Sprint, plus a plan for delivering the product Increment and realizing the Sprint Goal.
106 | Other people than the Scrum Team can attend the Sprint Planning in order to provide technical or domain advice. | multiple-choice | TRUE | FALSE |  |  |  |  | 1 | The Development Team may also invite other people to attend in order to provide technical or domain advice.
107 | Which best describes the Product Backlog? | multiple-choice | It provides just enough information to enable a Scrum team to start the design phase of a product. | It contains all foreseeable tasks and requirements form which the Scrum team can develop and maintain a complete project plan. | It is allowed to grow and change as more is learned about the products and its customers. | It is baselined to follow change management processes. |  |  | 3 | The Product Backlog evolves as the product and the environment in which it will be used evolves. The Product Backlog is dynamic; it constantly changes to identify what the product needs to be appropriate, competitive, and useful.
108 | It is normal to have a "hardening" Sprint to remove all technical debt and prepare the Product for upcoming release. | multiple-choice | TRUE | FALSE |  |  |  |  | 2 | It is not normal. Development Teams deliver an Increment of product functionality every Sprint. This Increment is usable, so a Product Owner may choose to immediately release it. So, there is nothing to prepare. Each increment contains only "Done" functionality that could be released immediately.
109 | An abnormal termination of a Sprint is called when? | multiple-choice | When it is clear at the end of a Sprint that everything won't be finished. | When the Team feels that the work is too hard. | When Sales has an important opportunity. | When the Product Owner determines that it makes no sense to finish it. |  |  | 4 | A Sprint would be cancelled if the Sprint Goal becomes obsolete.
110 | What happens if the Development Team cannot complete its work by the end of the sprint? | multiple-choice | The Sprint is extended temporarily. Lessons are taken to ensure it doesn't happen again. | The sprint is extended and future sprints use this new duration. | The sprint length holds and the Development Team continuously learns what is actually possible to do within a Sprint of this length. |  |  |  | 3 | Sprints have consistent durations throughout a development effort. A new Sprint starts immediately after the conclusion of the previous Sprint.
111 | How is management external to the Scrum Team involved in the Daily Scrum? | multiple-choice | The Scrum Master speaks on their behalf. | The Development Team self-manages and is the only management required at the Daily Scrum. All others cannot attend. | Management gives an update at the start of each Daily Scrum | The Product Owner represents their options. |  |  | 2 | The Development Team self-manages and is the only management required at the Daily Scrum. All others cannot attend.
112 | Drawing a trend line through a release burndown chart indicates? | multiple-choice | When the work remaining will likely be completed if nothing changes on the backlog or Development Team. | When all Sprint Backlog work will be completed and the Scrum Team will be released for other work. | Cost of the project. | When the project will be over if the Product Owner removes work that is equal in effort to any new work that is added. |  |  | 1 | When the work remaining will likely be completed if nothing changes on the backlog or Development Team.
113 | The Sprint Backlog is created at the Sprint Planning. It is prohibited to add new work into the Sprint Backlog later by the Development Team. | multiple-choice | TRUE | FALSE |  |  |  |  | 2 | The Development Team modifies the Sprint Backlog throughout the Sprint, and the Sprint Backlog emerges during the Sprint. This emergence occurs as the Development Team works through the plan and learns more about the work needed to achieve the Sprint Goal. As new work is required, the Development Team adds it to the Sprint Backlog.
114 | What provides guidance to the Development Team on why it is building the Increment? | multiple-choice | The Sprint Backlog | The Scrum Master | The Sprint Goal | The Product Owner |  |  | 3 | The Sprint Goal is an objective set for the Sprint that can be met through the implementation of Product Backlog. It provides guidance to the Development Team on why it is building the Increment.
115 | Scrum is based on empirical process control theory. All of its artifacts must be transparent to ensure sufficient accuracy of inspection. Which two measures ensures that the Product Backlog is transparent (Choose 2 answers)? | multi-select | The Product Backlog is ordered. | The Product Backlog only has work for the next 2 sprints. | The Product Backlog is managed using a web-based tool. | The Product Backlog is available to all stakeholders. |  |  | 1,4 | Scrum relies on transparency. Decisions to optimize value and control risk are made based on the perceived state of the artifacts.
116 | Who should make sure everyone on the Development Team does his or her tasks for the Sprint? | multiple-choice | The Project Manager. | The Product Owner. | The Scrum Master. | The Development Team. | All of above. |  | 4 | They are self-organizing.
117 | Why is important that there is only one Product Owner per product? (Choose 3 answer). | multi-select | Its clear for who is accountable for the ultimate successes of the product. | The Development Team always know who determine priorities. | Its helps the economy by increase employment. | Its helps avoid barriers to effective communication and rapid decision-making. | The Scrum Master knows who will be his backup whenever he goes in vacation. |  | 1,2,4 | The Product Owner is one person, not a committee. The Product Owner may represent the desires of a committee in the Product Backlog, but those wanting to change a Product Backlog item’s priority must address the Product Owner.
118 | Is it allowed to skip the Daily Scrum if there is nothing interesting to talk about? | multiple-choice | TRUE | FALSE |  |  |  |  | 2 | Each event in Scrum is a formal opportunity to inspect and adapt something. These events are specifically designed to enable critical transparency and inspection. Failure to include any of these events results in reduced transparency and is a lost opportunity to inspect and adapt.
119 | Which are NOT appropriate topics for a discussion in a Sprint Retrospective (Choose 2 answers). | multi-select | How the team does its work. | Team relations. | Definition of Done. | Sprint Backlog for the next Sprint. | The value of work currently represented in the Product Backlog. |  | 4,5 | The purpose of the Sprint Retrospective is to: Inspect how the last Sprint went with regards to people, relationships, process, and tools; Identify and order the major items that went well and potential improvements; and Create a plan for implementing improvements to the way the Scrum Team does its work.
120 | Which of the following statements is NOT true? | multiple-choice | The Product Backlog evolves as the product and the environment in which it will be used evolves. | The Product Backlog is dynamic. | The Product Backlog constantly changes to identify what the product needs to be. | The Product Backlog is complete when the final product Increment is considered "Done". |  |  | 4 | If a product exists, its Product Backlog also exists.
121 | Which of the following best describes an increment of working software? | multiple-choice | An automated test suite to verify functionality delivered in previous iterations. | UML diagrams that describe how to verify functionality delivered in previous iterations. | A decomposition of all Product Backlog Items into tasks for future backlog lists. | Additional features in a usable state that complement those delivered in previews iterations. |  |  | 4 | The Increment is the sum of all the Product Backlog items completed during a Sprint and the value of the increments of all previous Sprints
122 | What are the two essential features a Scrum Team should possess? | multi-select | It should choose how best to accomplish their work, rather than being directed by others outside the team. | It should use tools, processes and techniques approved by the Organization. | It should be flexible enough to complete all the work planned for the Sprint even if some team members are on vacation. | It should have all competencies needed to accomplish the work without depending on others not part of the team. |  |  | 1,4 | Scrum Teams are self-organizing and cross-functional. Self-organizing teams choose how best to accomplish their work, rather than being directed by others outside the team. Cross-functional teams have all competencies needed to accomplish the work without depending on others not part of the team.
123 | Who is responsible for promoting and supporting Scrum? Select the best choice. | multiple-choice | The Product Owner | The Scrum Master | The Scrum Team | The Scrum Master and the Product Owner | The Development Team |  | 2 | The Scrum Master is responsible for promoting and supporting Scrum as defined in the Scrum Guide. Scrum Masters do this by helping everyone understand Scrum theory, practices, rules, and values.
124 | Scrum recommends using only those Scrum components and rules which suit most for a particular project. | multiple-choice | TRUE | FALSE |  |  |  |  | 2 | Each component within the Scrum framework serves a specific purpose and is essential to Scrum’s success and usage.
125 | Please select which statement is the MOST accurate: | multiple-choice | Refinement is a part-time activity during a Sprint between the Product Owner and the Development Team. | Refinement is a full-time activity during a Sprint for the Scrum Team. | Refinement is a part-time activity during a Sprint between the Product Owner and the Scrum Master. | Refinement is a full-time activity during a Sprint between the Product Owner and the Development Team. |  |  | 1 | The Scrum Team decides how and when refinement is done. Refinement usually consumes no more than 10% of the capacity of the Development Team.
126 | Imagine the following situation. At the Sprint Retrospective meeting the Scrum Team identified some improvements that can be done. What should the Scrum Team do? Select the best option. | multiple-choice | Assign a responsible team member for at least one improvement. Check the progress at the next Retrospective. | Make sure the Sprint Backlog for the next Sprint includes at least one high priority process improvement. | Make sure the Sprint Backlog for the next Sprint includes all the improvements. | Assign responsible team members for every improvement. Check the progress at the next Retrospective. |  |  | 2 | The Sprint Backlog makes visible all the work that the Development Team identifies as necessary to meet the Sprint Goal. To ensure continuous improvement, it includes at least one high priority process improvement identified in the previous Retrospective meeting.
127 | For which is the Scrum Master responsible? | multiple-choice | The Scrum Team meeting and the objectives it sets for itself. | Managing the performance of the Scrum Team. | The Scrum process being adopted and used properly. | Keeping track of resource allocation. |  |  | 3 | The Scrum Master is responsible for promoting and supporting Scrum as defined in the Scrum Guide.
128 | Which statement best describes a Product Owner's responsibility? | multiple-choice | Optimizing the value of the work the Development Team does. | Directing the Development Team. | Managing the project and ensuring that the work meets the commitments to the stakeholders. | Keeping stakeholders at bay. |  |  | 1 | The Product Owner is responsible for maximizing the value of the product and the work of the Development Team.
129 | Development Team members volunteer to own a Sprint Backlog item: | multiple-choice | At the Sprint planning meeting. | Never. All Sprint Backlog Items are "owned" by the entire Development Team, even though each one may be done by an individual development team member. | Whenever a team member can accommodate more work | During the Daily Scrum. |  |  | 2 | Sprint Backlog and all of its items are collectively owned by the Development Team. No individual team member can claim ownership over an item as this would block communication and collaboration.
130 | What is included in the Sprint Backlog? | multiple-choice | User stories | Tasks | Use Cases | Tests | Any of the above (or others) which is a decomposition of the selected Product Backlog items. |  | 5 | The Sprint Backlog is the set of Product Backlog items selected for the Sprint, plus a plan for delivering the product Increment and realizing the Sprint Goal.
131 | What could be a source of requirements for any changes to be made to the product? | multi-select | The CEO of the Organization | The Key Stakeholders | The Product Backlog |  |  |  | 3 | The Product Backlog is an ordered list of everything that might be needed in the product and is the single source of requirements for any changes to be made to the product.
132 | What happens when a Sprint is cancelled? Select three. | multi-select | Several top Product Backlog Items are taken into the Sprint Backlog to replace the obsolete items. | Any completed and "Done" Product Backlog items are reviewed. | All incomplete Product Backlog Items are re-estimated and put back on the Product Backlog. | At the Sprint Retrospective the Scrum Master determines who from the Development Team is responsible for cancelling the Sprint. | If part of the work is potentially releasable, the Product Owner typically accepts it. |  | 2,3,5 | When a Sprint is cancelled, any completed and "Done" Product Backlog items are reviewed. If part of the work is potentially releasable, the Product Owner typically accepts it. All incomplete Product Backlog Items are re-estimated and put back on the Product Backlog.
133 | Are all of the following types of requirements acceptable on a Product Backlog [Stability Requirements, Performance requirements, Product Functionality, Documentation, Fixes]? | multiple-choice | TRUE | FALSE |  |  |  |  | 1 | Every work that can bring value to product can be in Product Backlog.
134 | Could the Sprint Planning be finished if only work planned for the first days of the Sprint is decomposed to units of one day or less? | multiple-choice | Yes, if the remaining work is also estimated, maybe in bigger units. | No, all items in the Sprint Backlog should be decomposed to units of one day or less by the end of the Sprint Planning. |  |  |  |  | 1 | The Scrum Guide requires only the work planned for the first days of the Sprint is decomposed by the end of the Sprint Planning, often to units of one day or less. However, the Development Team should be able to explain to the Product Owner and Scrum Master how it intends to work as a self-organizing team to accomplish the Sprint Goal and create the anticipated Increment.
135 | During a Sprint, when is new work or further decomposition of work added to the Sprint Backlog? | multiple-choice | When the Product Owner identifies a new work. | As soon as possible after they are identified. | When the Scrum Master has time to enter them. | During the Daily Scrum after the Development Team approves them. |  |  | 2 | As new work is required, the Development Team adds it to the Sprint Backlog.
136 | Could the Product Owner and the Scrum Master be a part of the Development Team? | multiple-choice | TRUE | FALSE |  |  |  |  | 1 | Scrum does not prohibit the Product Owner or the Scrum Master do development work. However, it is not the best practice because it could create a conflict of interest.
137 | The Development Team should not be interrupted during the Sprint. The Sprint Goal should remain intact. These are conditions that foster creativity, quality and productivity. Based on this, which of the following is FALSE? | multiple-choice | The Product Owner can help clarify or optimize the Sprint when asked by the Development Team. | The Sprint Backlog is fully formulated in the Sprint Planning meeting and does not change during the Sprint. | As a decomposition of the selected Product Backlog Items, the Sprint Backlog changes and may grow as the work emerges. | The Development Team may work with the Product Owner to remove or add work if it finds it has more or less capacity than it expected. |  |  | 2 | The Sprint Backlog makes visible all of the work that the Development Team identifies as necessary to meet the Sprint Goal. The Development Team modifies the Sprint Backlog throughout the Sprint, and the Sprint Backlog emerges during the Sprint.
138 | A burndown chart tracks? | multiple-choice | Work remaining across time | Accumulated cost on a Project. | Individual worker productivity. | Accumulated business value delivered to the customer. |  |  | 1 | Work remaining across time
139 | If quality assurance work does not occur as part of the development work within a Sprint, which benefits are lost? | multi-select | The increment probably is not potentially shippable. | The project manager cannot effectively update the plan. | The product backlog burndown is not transparent. | The next Sprint will probably be interrupted with bugs that are being found. |  |  | 1,4 | As the answers
140 | Scrum does not have a role called "project manager." | multiple-choice | TRUE | FALSE |  |  |  |  | 1 | A Scrum Team has a Scrum Master, a Product Owner and a Development Team. As a whole they have all controls needed.
141 | Who creates the increment? | multiple-choice | The Development Team | The Product Owner | The Development Team and The Product Owner | The Scrum Team | The Scrum Master |  | 1 | Only members of the Development Team create the Increment.
142 | Upon what type of process control is Scrum based? | multiple-choice | Empirical | Hybrid | Defined | Complex |  |  | 1 | Scrum is founded on empirical process control theory, or empiricism. Empiricism asserts that knowledge comes from experience and making decisions based on what isknown.
143 | An abnormal termination of a Sprint is called when the Development Team realizes that the work is too hard for their skillset. | multiple-choice | TRUE | FALSE |  |  |  |  | 2 | A Sprint would be cancelled if the Sprint Goal becomes obsolete.
144 | What is the maximum length of a Sprint? | multiple-choice | Not so long that the risk is unacceptable to the Product Owner. | Not so long that other business events can't be readily synchronized with the development work. | No more than one calendar month. | All of these answers are correct. |  |  | 4 | All of these answers are correct.
145 | The purpose of a Sprint is to produce a done increment of working product. | multiple-choice | TRUE | FALSE |  |  |  |  | 1 | The heart of Scrum is a Sprint, a time-box of one month or less during which a "Done", usable, and potentially releasable product Increment is created.
146 | Scrum Master is a “management” position? | multiple-choice | TRUE | FALSE |  |  |  |  | 1 | The Scrum Master manages the Scrum process. If the Scrum Master is not a management position, he or she may not have the influence to remove impediments. The Scrum Master does not manage the team.
147 | Who is allowed to change the Sprint Backlog during the Sprint? | multiple-choice | The Scrum Team. | The Development Team. | The Product Owner. | The Scrum Master. | The Development Team and the Product Owner. |  | 2 | Only the Development Team can change its Sprint Backlog during a Sprint. The Sprint Backlog is a highly visible, real-time picture of the work that the Development Team plans to accomplish during the Sprint, and it belongs solely to the Development Team.
148 | How frequently should scrum users inspect Scrum artifacts and progress toward a Sprint Goal? | multiple-choice | After the Daily Scrum. | As frequently as possible. | Frequently, but it should not get in the way of the work. | At the Sprint Review. |  |  | 3 | Scrum users must frequently inspect Scrum artifacts and progress toward a Sprint Goal to detect undesirable variances. Their inspection should not be so frequent that inspection gets in the way of the work. Inspections are most beneficial when diligently performed by skilled inspectors at the point of work.
149 | The three pillars of empirical process control are: | multiple-choice | Respect For People, Kaizen, Eliminating Waste | Planning, Demonstration, Retrospective | Inspection, Transparency, Adaptation | Planning, Inspection, Adaptation | Transparency, Eliminating Waste, Kaizen |  | 3 | Scrum is founded on empirical process control theory, or empiricism. Empiricism asserts that knowledge comes from experience and making decisions based on what is known. Three pillars uphold every implementation of empirical process control: transparency, inspection, and adaptation.
150 | Who is responsible for creation of the Definition of "Done"? | multiple-choice | The Development Team | The Scrum Master | The Product Owner | The Scrum Team |  |  | 1 | If the definition of "done" for an increment is part of the conventions, standards or guidelines of the development organization, all Scrum Teams must follow it as a minimum. If "done" for an increment is not a convention of the development organization, the Development Team of the Scrum Team must define a definition of "done" appropriate for the product. If there are multiple Scrum Teams working on the system or product release, the development teams on all of the Scrum Teams must mutually define the definition of "Done".
151 | What are criteria to order Product Backlog Items? | multiple-choice | Value of Product Backlog Items. | Dependencies between Product Backlog Items. | Dependencies to other products. | All of the above. |  |  | 1 | The Product Owner is responsible for maximizing the value of the product resulting from work of the Development Team.
152 | What comprises Scrum (select four)? | multi-select | Artifacts | Reports | Burn-down charts | Roles | Rules | Events | 1,4,5,6 | The Scrum framework consists of Scrum Teams and their associated roles, events, artifacts, and rules. Each component within the framework serves a specific purpose and is essential to Scrum’s success and usage. The rules of Scrum bind together the events, roles, and artifacts, governing the relationships and interaction between them.
153 | What is the essence of Scrum? Select the most appropriate option. | multiple-choice | A small team of people that is highly flexible and adaptive | The Scrum Guide | The Development Team | The Scrum Master and the Product Owner |  |  | 1 | The essence of Scrum is a small team of people. The individual team is highly flexible and adaptive. These strengths continue operating in single, several, many, and networks of teams that develop, release, operate and sustain the work and work products of thousands of people. They collaborate and interoperate through sophisticated development architectures and target release environments.
154 | When does the next Sprint begin? | multiple-choice | Next Monday. | Immediately following the next Sprint Planning. | When the Product Owner is ready. | Immediately after the conclusion of the previous Sprint. |  |  | 4 | A new Sprint starts immediately after the conclusion of the previous Sprint.
155 | What is a Development Team responsible for? | multiple-choice | Organizing the work required to meet the Sprint Goal. | Reporting productivity. | Resolving internal team conflicts. | Selecting the Product Owner. |  |  | 1 | A Development Team responsible for organizing the work required to meet the Sprint Goal.
156 | Who participates in the Sprint Planning? Select three. | multi-select | The Scrum Master | The Product Owner | The Development Team | The Key Stakeholders | The Team Manager |  | 1,2,3 | The work to be performed in the Sprint is planned at the Sprint Planning. This plan is created by the collaborative work of the entire Scrum Team.
157 | The Daily Scrum always should take exactly 15 minutes. For example, if your team managed doing it in 5 minutes, you should spend 10 more minutes on some useful team activity like Product Backlog refinement, but not more. | multiple-choice | TRUE | FALSE |  |  |  |  | 2 | All events in Scrum are time-boxed. It means that every event has a maximum duration. However, the Scrum Guide does not require a minimal duration for any event. As Scrum Teams mature, they can do some events faster (e.g. the Sprint Planning or the Sprint Retrospective).
158 | A properly functioning Scrum team will have at least one Release Sprint and may well have several. | multiple-choice | TRUE | FALSE |  |  |  |  | 2 | Each Sprint create an Increment
159 | Which two things does a Scrum Master do if the Development Team doesn’t have the engineering tools and infrastructure to completely finish any Product Backlog Items? | multi-select | Declares the Development Team not ready for Scrum. | Ask the development Team to spend as many Sprints as necessary to prepare the engineering tools and infrastructure so any Product Backlog item it selects is potentially shippable at Sprint end. | Asks the Development Team to do the best it can on each Product Backlog item it selects. | Has the Development Team Define “Done” and do the same work for all Product Backlog items it selects. | Has the Development Team improves its skills, tools and infrastructure over time and adjust the definition of “Done” accordingly. |  | 2,5 | As the answers
160 | Check all the formal opportunities to inspect and adapt. | multi-select | The Sprint Retrospective. | The Daily Scrum. | The Sprint Review. | The Sprint Planning. | The Sprint. |  | 1,2,3 | Other than the Sprint itself, which is a container for all other events, each event in Scrum is a formal opportunity to inspect and adapt something. These events are specifically designed to enable critical transparency and inspection.
161 | How much time does the Sprint Planning take? | multiple-choice | Not more than 8 hours | As much as it is necessary to make task break-down and estimations for all items in the Sprint Backlog | From 4 to 8 hours | Not more than 4 hours |  |  | 1 | Sprint Planning is time-boxed to a maximum of eight hours for a one-month Sprint.
162 | The Development Team should be able to explain to the Product Owner and Scrum Master how it intends to work as a self-organizing team to accomplish the Sprint Goal and create the anticipated Increment. | multiple-choice | TRUE | FALSE |  |  |  |  | 1 | By the end of the Sprint Planning, the Development Team should be able to explain to the Product Owner and Scrum Master how it intends to work as a self-organizing team to accomplish the Sprint Goal and create the anticipated Increment.
163 | What is the recommended size for a Development Team (within the Scrum Team)? | multiple-choice | Minimal 7 | 3 to 9 | 7 plus or minus 2 | 9 |  |  | 2 | Optimal Development Team size is small enough to remain nimble and large enough to complete significant work. Fewer than three Development Team members decreases interaction and results in smaller productivity gains. More than nine members simply requires too much coordination.
164 | Imagine you are a Scrum Master. There are 10 professionals (developers and QAs) and the Product Owner. How do you distribute people between development teams? Choose all applicable options: | multi-select | 2 teams of 6 and 4 people (because it is good to have all the QAs in a separate team) | 1 team of 10 people (because there is no reason to divide) | 3 teams of 4, 3 and 3 people (each team is cross-functional) | 2 teams of 6 and 4 people (the professionals after a short meeting decided this is the best option) |  |  | 3,4 | Optimal Development Team size is small enough to remain nimble and large enough to complete significant work within a Sprint. Fewer than three Development Team members decrease interaction and results in smaller productivity gains. Having more than nine members requires too much coordination. The Product Owner and Scrum Master roles are not included in this count unless they are also executing the work of the Sprint Backlog.
165 | The length of a Sprint should be: | multiple-choice | Short enough to keep the business risk acceptable to the Product Owner. | Short enough to be able to synchronize the development work with other business events. | No more than one calendar month. | All of these answers are correct |  |  | 4 | All of these choices are appropriate considerations in determining the length of a Sprint.
166 | What is Scrum? | multiple-choice | A framework within which people can address complex adaptive problems, while delivering valuable products. | A sequential design process, used in software development processes, in which progress is seen as flowing steadily downwards. | A software development methodology which is intended to improve software quality. | A cookbook that defines best practices for software development | A complete methodology that defines how to develop software. | A defined and predictive process that conforms to the principles of Scientific Management. | 1 | A framework within which people can address complex adaptive problems, while delivering valuable products.
167 | What is the best suited structure for Development Teams in order to produce integrated increments? | multiple-choice | Each Development Team work in only on technical layer of the system. | Each Development Team develops functionality from beginning to end through all technical layers. |  |  |  |  | 2 | It is cross-functional & self-organizing
168 | Which topics should be discussed in the Sprint Review? | multiple-choice | The Scrum process, and how it was used during the Sprint. | Coding and engineering pratices. | Sprint results. | All of the above. |  |  | 3 | All of the above.
169 | Select the two meetings in which people outside the Scrum Team are allowed to participate. | multi-select | The Sprint Retrospective. | The Sprint Planning. | The Sprint Review. | The Daily Scrum. |  |  | 2,3 | The Development Team may invite other people to attend the Sprint Planning in order to provide technical or domain advice. The Product Owner is responsible for inviting the Key Stakeholders to the Sprint Review meeting.
170 | What are Product Backlog features? Select three. | multi-select | As long as a product exists, its Product Backlog also exists. | When the final version of a product is rolled out, its Product Backlog is dismissed. | It is dynamic. | It is never complete. | A Product Backlog could be closed when it contains no items to include into the next Sprint. |  | 1,3,4 | A Product Backlog is never complete. The earliest development of it only lays out the initially known and best-understood requirements. The Product Backlog evolves as the product and the environment in which it will be used evolves. The Product Backlog is dynamic; it constantly changes to identify what the product needs to be appropriate, competitive, and useful. As long as a product exists, its Product Backlog also exists.
171 | Which two (2) things does the Development Team do during the first Sprint? | multi-select | Deliver an increment of releasable software. | Determine the complete architecture and infrastructure for the product. | Develop and deliver at least one piece of functionality. | Develop a plan for the rest of the release. | Create the complete Product Backlog to be developed in subsequent Sprints. |  | 1,3 | The heart of Scrum is a Sprint, a time-box of one month or less during which a "Done", useable, and potentially releasable product Increment is created. This applies to every Sprint.
172 | What should be taken into account for the Definition of "Done"? Select the two most appropriate items. | multi-select | Definition of "Done" of other Scrum Teams working on other products. | Experience of the Product Owner. | Definition of "Done" of other Scrum Teams working on the same Product. | Conventions, standards and guidelines of the Organization. | Advice of the Scrum Master. |  | 3,4 | If the definition of "done" for an increment is part of the conventions, standards or guidelines of the development organization, all Scrum Teams must follow it as a minimum. If "done" for an increment is not a convention of the development organization, the Development Team of the Scrum Team must define a definition of "done" appropriate for the product. If there are multiple Scrum Teams working on the system or product release, the development teams on all of the Scrum Teams must mutually define the definition of "Done".
173 | What are the questions the Sprint Planning answers? Select two. | multi-select | How will the work needed to deliver the Increment be achieved? | What can be delivered in the Increment resulting from the upcoming Sprint? | Who will be responsible for each item in the Sprint Backlog? | What is the size of the Technical Debt and how it could be removed? | What new technologies could be used to speed up the Development Team velocity? |  | 1,2 | Sprint Planning answers the following: What can be delivered in the Increment resulting from the upcoming Sprint? & How will the work needed to deliver the Increment be achieved?
174 | During a Sprint Retrospective, for what is the Scrum Master responsible? | multiple-choice | Acting as a scribe to capture the Development Team’s answers. | Summarizing and reporting the discussions to management. | Prioritizing the resulting action items. | Participating as a Scrum Team member, and facilitating as requested or needed. |  |  | 4 | The Scrum Master participates as a peer team member in the meeting from the accountability over the Scrum process.
175 | How does the Scrum Master serve the Organization? Select the three most appropriate answers. | multi-select | Making sure the key stakeholders are invited on all Scrum Reviews within organization | Working with other Scrum Masters to increase the effectiveness of the application of Scrum in the organization | Planning Scrum implementations within the organization | Leading and coaching the organization in its Scrum adoption | Mixing experienced developers and junior specialists across different Development Teams in the organization to speed up Scrum adoption |  | 2,3,4 | The Scrum Master serves the organization in several ways, including: Leading and coaching the organization in its Scrum adoption; Planning Scrum implementations within the organization; Helping employees and stakeholders understand and enact Scrum and empirical product development; Causing change that increases the productivity of the Scrum Team; and Working with other Scrum Masters to increase the effectiveness of the application of Scrum in the organization.
176 | What are three things might a Scrum Product Owner focus on to ensure his product delivers value? (Choose 3 answers). | multi-select | How readily his product can be absorbed and used by his customers. | The size of the product in lines of code. | How much of the functionality of his product is being utilized. | Direct customer feedback. | Minimizing changes to project scope. |  | 1,3,4 | Understanding user is the key to product success.
177 | All Development Teams working on the same Product should use the same Product Backlog. | multiple-choice | TRUE | FALSE |  |  |  |  | 1 | Multiple Scrum Teams often work together on the same product. One Product Backlog is used to describe the upcoming work on the product.
178 | Which statement best describes the Sprint Review? | multiple-choice | It is a mechanism to control the Development Team's activities during a Sprint. | It is when the Scrum Team and stakeholders inspect the outcome of a Sprint and figure out what to do next. | It is a demo at the end of the Sprint for everyone in the organization to check on the work done. |  |  |  | 2 | Every event in Scrum, besides the Sprint which is a container for the other events, is an opportunity to Inspect AND Adapt.
179 | A product increment must be released to production at the end of each Sprint. | multiple-choice | TRUE | FALSE |  |  |  |  | 2 | Product Owner will release when it make sense
180 | During a Sprint, a Development Team determines that it will not be able to finish the complete forecast. Who should be present to review and adjust the Sprint work selected? | multiple-choice | The Scrum Master, the project manager and the Development Team. | The Product Owner and the Development Team. | The Product Owner and all stakeholders. | The Development Team. |  |  | 2 | During the Sprint, scope may be clarified and re-negotiated between the Product Owner and Development Team as more is learned.
181 | Who is responsible for tracking the total work remaining in the Sprint Backlog to project the likelihood of achieving the Sprint Goal? | multiple-choice | The Product Owner. | The Scrum Master. | The Development Team. | The Scrum Team. | The Product Owner and the Development Team. |  | 3 | At any point in time in a Sprint, the total work remaining in the Sprint Backlog can be summed. The Development Team tracks this total work remaining at least for every Daily Scrum to project the likelihood of achieving the Sprint Goal. By tracking the remaining work throughout the Sprint, the Development Team can manage its progress.
182 | How much work must a Development Team do to a Product Backlog Item in select for a sprint? | multiple-choice | As much as it has told the Product Owner will be done for every Product Backlog item it selects in conformance with the definition of done. | As much as it can fit into the Sprint. | All development work and at least some testing. | Analysis, design, programming, testing and documentation. |  |  | 1 | The purpose of each Sprint is to deliver Increments of potentially releasable functionality that adhere to the Scrum Team's current definition of "Done".
183 | Why does the Product Owner want the Development Team do adhere to its definition of "Done"? | multiple-choice | To predict the team's productivity over time. | To know what the team will deliver over the next three sprints. | To be able to reprimand the team when they don't meet their velocity goal for the Sprint. | To have complete transparency into what has been done at the end of each Sprint. |  |  | 4 | To have complete transparency into what has been done at the end of each Sprint.
184 | Which of the following is the Development Team NOT responsible for? | multiple-choice | Selecting the Product Owner. | Resolving internal conflicts. | Planning how to meet a Sprint goal. | Monitoring and increasing productivity. | Monitoring and optimizing the work required to meet the Sprint goal at least daily. |  | 1 | Selecting the Product Owner.
185 | If an item in the Sprint Backlog cannot be finished by the end of the Sprint (it turned out there is a lot more work to do than was estimated), the Sprint is cancelled. | multiple-choice | TRUE | FALSE |  |  |  |  | 2 | The Sprint is cancelled only in the case if the Sprint Goal became obsolete. If some work could not be done, the Sprint Backlog should be re-negotiated between the Product Owner and Development Team.
186 | Who is allowed to make changes in the Product Backlog? | multi-select | The Product Owner | The Development Team, but with permission of the Product Owner | Anyone | The Key Stakeholders |  |  | 1,2 | The Product Owner is the sole person responsible for the Product Backlog. However, he or she can delegate some work related to product backlog management to the Development Team.
187 | Only the Product Owner and the Development Team participate in the Sprint Planning. There is nothing to do for the Scrum Master. | multiple-choice | TRUE | FALSE |  |  |  |  | 2 | The work to be performed in the Sprint is planned at the Sprint Planning. This plan is created by the collaborative work of the entire Scrum Team.
188 | As the Sprint Planning meeting progresses, the workload is getting to be greater than the Development Team’s capacity. Which two actions make the most sense to do? | multi-select | Cancel the Sprint. | Start the Sprint and recruit additional Development Team members. | Potentially remove or change selected Product Backlog items. | The Development Team should ensure that the Production Owner is aware. Then, start the Sprint and monitor burndown rates. | Ask the Development Team to work overtime for this Sprint and promise that it won’t happen again. |  | 3,4 | The number of items selected from the Product Backlog for the Sprint is solely up to the Development Team.
189 | All the Scrum Teams working on the same product should have the same Sprint length. | multiple-choice | TRUE | FALSE |  |  |  |  | 2 | False. Scrum does not require having aligned Sprints for multiple teams.
190 | How small should a "ready" Product Backlog Item be? | multiple-choice | Small enough to build in 1 sprint. | No longer than 1 day. | No bigger than 8 story points. | It should fit to a small index card. |  |  | 1 | It must be fit in one Sprint
191 | What is the Sprint Backlog? | multiple-choice | The Product Backlog items selected for this Sprint plus the plan for delivering them. | The Product Backlog items selected for this Sprint. | The Product Backlog items selected for this Sprint plus a set of Development Team internal tasks. |  |  |  | 1 | The Sprint Backlog is the set of Product Backlog items selected for the Sprint, plus a plan for delivering the product Increment and realizing the Sprint Goal.
192 | The Product Backlog is ordered by: | multiple-choice | Size, where small items are at the top and large items are at the bottom. | Risk, where safer items are at the top, and riskier items are at the bottom. | Least valuable items at the top to most valuable at the bottom. | Items are randomly arranged. | Whatever is deemed most appropriate by the Product Owner. |  | 5 | The Product Owner decides what makes the most sense to optimize the value of the work being done by the Development Team.
193 | What are the three questions the Scrum Guide gives as an example that can be used at the Daily Scrum? | multi-select | Do I have complete understanding of the Sprint Backlog item I am working on? | What will I do today to help the Development Team meet the Sprint Goal? | What did I do yesterday that helped the Development Team meet the Sprint Goal? | Do I see any impediment that prevents me or the Development Team from meeting the Sprint Goal? | Did I explain all the discovered issues I found yesterday to the Product Owner? |  | 2,3,4 | The structure of the Daily Scrum is set by the Development Team and can be conducted in different ways if it focuses on progress toward the Sprint Goal. Some Development Teams will use questions, some will be more discussion based. Here is an example of what might be used: What did I do yesterday that helped the Development Team meet the Sprint Goal?; What will I do today to help the Development Team meet the Sprint Goal?; Do I see any impediment that prevents me or the Development Team from meeting the Sprint Goal?
194 | What are some consequences if a Development Team does not have a consistent definition of done from Sprint to Sprint? | multiple-choice | The Development team may not know how many Product Backlog items it can do in a Sprint. | The Product Owner may not know what he/she is inspecting at the Sprint Review. | The Product Owner may be unable to get gauge the progress toward his/her goals. | The Development Team may not know what work is entailed in completing selected Product Backlog items. | All of above |  | 5 | All of above
195 | Which of the following are true about the length of the Sprint ? (Select all that apply.) | multi-select | Sprint length is determined during Sprint Planning, and should be long enough to make sure the Development Team can deliver what is to be accomplished in the upcoming Sprint. | It is best to have Sprints of consistent length throughout a development effort. | The length of the Sprint should be proportional to the work that is done in between Sprints. | Sprint length is determined during Sprint Planning, and should hold the time it will take to code the planned features in the upcoming Sprint, but does not include time for any testing. | All Sprints must be 1 month or less. |  | 2,5 | Sprints have consistent durations throughout a development effort.
196 | Please select the option(s) that NOT adhere to the purpose of Sprint Retrospective: | multi-select | Create a plan for implementing improvements to the way the Scrum Team does its work. | Finding ways to increase product quality by adapting the Definition of "Done" as appropriate. | Inspect how the product increment satisfies the Product Backlog items. | Identify and order the major items that went well and list the potential improvements. |  |  | 2 | Retrospective section in Scrum Guide
197 | The Scrum Team consists of | multi-select | The Development Team | The Product Owner | The Scrum Master | The Key Stakeholders | Users | Project Manager | 1,2,3 | The Scrum Team consists of the Scrum Master (manages the process), the Product Owner (decides what to do) and the Development Team (does the work).
198 | What is the input to the Sprint Planning? Select four. | multi-select | The latest product Increment | Feedback from the Key Stakeholders | Projected capacity of the Development Team during the Sprint | The Product Backlog | Feedback from the Organization CEO | Past performance of the Development Team | 1,3,4,6 | The input to the Sprint Planning is the Product Backlog, the latest product Increment, projected capacity of the Development Team during the Sprint, and past performance of the Development Team.
199 | Select two ways to maintain the Product Backlog to maximize its transparency. | multi-select | Product Backlog Items are sized appropriately, not bigger than a sprint and a preference for several do-able items in a sprint. | Product Backlog is only updated at the Sprint Review, when both the Scrum Team and the stakeholders are available. | Product Backlog is only updated at a release planning meeting with stakeholders and the release train engineers present. | The Product Backlog always has the most actual insights. |  |  | 1,4 | The Product Backlog lists all features, functions, requirements, enhancements, and fixes that constitute the changes to be made to the product in future releases. Product Backlog items have the attributes of a description, order, estimate, and value. Product Backlog items often include test descriptions that will prove its completeness when “Done.
200 | Sort Scrum events in the right order. | multiple-choice | Sprint Planning - Daily Scrum - Sprint Review - Sprint Retrospective. | Sprint Planning - Daily Scrum - Sprint Retrospective - Sprint Review. | Sprint Review - Sprint Planning - Daily Scrum - Sprint Retrospective. | Sprint Review - Daily Scrum - Sprint Retrospective - Sprint Planning. | Sprint Planning - Sprint Review - Daily Scrum - Sprint Retrospective. | Sprint Retrospective - Sprint Planning - Daily Scrum - Sprint Review. | 1 | A sprint begins with Sprint Planning, then there are several Daily Scrum meetings following by Sprint Review and then Sprint Retrospective.